## Sheet1
PRODUCT BACKLOG REPORT: FinTrack
ID | Who | Why | What | PRIORITY | PRIORITY LEVEL | STATUS
UOB-1 | End-user | To quickly use the app | As a user, I want to sign up and sign in with Email | High | 5 | In Progress
UOB-2 | End-user | To organize financial data for better management and analysis. | As a user, I want to categorize my transactions into predefined or custom categories, so that I can organize my finances better. | High | 5 | In Progress
UOB-3 | End-user | To keep track of financial transactions accurately and efficiently. | As a user, I want to add a new income or expense with details such as amount, date, category, and notes, so that I can keep track of my financial transactions. | High | 5 | In Progress
UOB-4 | End-user | To understand financial status at a glance. | As a user, I want to view a summary of my monthly income and expenses on the dashboard, so that I can understand my financial situation quickly | High | 5 | In Progress
UOB-5 | End-user | To manage and control spending effectively. | As a user, I want to set up monthly budgets for different categories and see real-time progress, so that I can manage my spending within set limits | High | 5 | In Progress
UOB-6 | End-user | get used to core functionality of the app. | As a user, I want to receive instructions on how to use the app. | High | 4 | In Progress
UOB-7 | End-user | get into core functionality of the app before personalizing profile | be able to skip the instruction if already familiar with the app. | High | 4 | In Progress
UOB-8 | End-user | start using the app with current Google account. | As a user, I want to sign in with personal Google Account. | High | 4 | In Progress
UOB-9 | End-user | Flexibility in using the application through multiple accounts. | As a user, I want to log out of current account. | High | 4 | In Progress
UOB-10 | End-user | To keep track of the savings process to meet the financial goals. | As a user, I want to see visual reports of saving by category and over time, so that I can analyze my financial habits and saving goal. | High | 4 | In Progress
UOB-11 | End-user | To prevent overspending and stay within budget | As a user, I want to receive notifications when I’m close to exceeding my budget, so that I can adjust my spending accordingly. | Medium | 3 | In Progress
UOB-12 | End-user | To ensure data availability and security across multiple devices | As a user, I want to securely sync my data across multiple devices, so that I can safely synchronize my financial information anywhere and ensure it is backed up | Medium | 3 | In Progress
UOB-13 | End-user | Increase experience and excitement when using the application | As a user, I want to receive a welcome notice for the first time using the app. | Medium | 3 | In Progress
UOB-14 | End-user | To manage debts, loans and payment processes effectively. | As a user, I want a management page that clearly shows all my debts, loans, and payments. This way, I can easily keep track of what I owe and what I have paid, helping me manage my money more effectively and stay on top of my financial responsibilities. | Medium | 3 | In Progress
UOB-15 | End-user | To instantly and conveniently manage spending. | As a user, I want a feature that when I take a picture of a receipt, it will automatically process an organized database for management. | Medium | 3 | In Progress
UOB-16 | End-user | To conveniently track the exchange rate for travel mode. | As a user, I want to see the up-to-date exchange rate of all currencies. | Medium | 3 | In Progress
UOB-17 | End-user | To reflect on bad or suboptimal product experiences so that the product can be improved. | As a user, I want to send reports about any issues or problems arise with description and images. | Medium | 3 | In Progress
UOB-18 | End-user | To customize the application to personal preferences for a better user experience. | As a user, I want to customize the app’s themes and settings, so that I can personalize my experience according to my preferences | Low | 2 | In Progress
MANUAL | End-user | Learn and understand how to utilize the software. | Software User Manual | High | 4 | In Progress
VISON | Product Owner | follow the legal rules from government about user identification | wants users to add more personal information when using the application | High | 4 | In Progress
PROCESS DEF | Product Owner | Project management regulates project work processes | Process Definition | High | 5 | In Progress
TEST PLAN | Dev team | Perform testing and ensure software quality | Test Plan document | High | 5 | In Progress
SPRINT REPORT | Scrum master | Project management, software development process management | Weekly Reports about Sprints. | High | 5 | In Progress
PRODUCT BACKLOG | Product Owner | Manage requests and track progress | "Product Backlog” document | High | 5 | In Progress
SPRINT BACKLOG | Scrum master | Assign tasks and monitor progress. | “Sprint Backlog” document | High | 5 | In Progress
RELEASE BACKLOG | Product Owner | Estimate the release schedule and track task completion status. | “Release Backlog” document | High | 5 | In Progress
BURNDOWN | Scrum master | Visualize the work progress and performance levels. | “Burndown Chart” document | High | 5 | In Progress
SOURCE | Product Owner | Easily alter and distribute the program to the intended audience. | Source code repository(FlutterFlow) | High | 5 | In Progress
VISION | Product Owner | Project management involves storing the project's greatest needs. | “Project vision and scope” documents | High | 5 | In Progress
CHARTER | Product Owner | Project management, work assignment | “Project Mandate” documents | High | 5 | In Progress
SUMMARY | Product Owner | Project management, quick grasp | “Project Summary” document | High | 5 | In Progress
FEASIBILITY | Product Owner | Project management and feasibility survey | Feasibility study report | High | 5 | In Progress
POC | Product Owner | Demonstrate project capabilities by addressing difficulties | Documentation, source code, demo. Implementation proof | High |  | In Progress
TOTAL
STATUS | PRIORITY LEVEL | PRIORITY
Not Started | 5 | High
In Progress | 4 | Medium
Complete | 3 | Low
Overdue | 2
On Hold | 1